## Slide 1
🌿
Wallah We Can
GreenSchool E-Commerce Platform
Project Status · User Guide · Roadmap for Completion
March 2026 | Confidential
Wallah We Can – GreenSchool E-Commerce Platform | Confidential
1 / 20

## Slide 2
Agenda
What we will cover in this presentation
01
The Mission & Platform Overview
What WWC is building and why
02
What Has Been Built
Complete feature inventory — backend, frontend, admin
03
Customer Journey — User Guide
Step-by-step walkthrough for shop visitors
04
Admin & Operations Guide
How the WWC team manages the shop
05
What Is Still Missing
Honest gap analysis — critical, high, medium priority
06
Roadmap for a Third-Party Developer
Phase 3 & 4 tasks with effort estimates
07
Technical Handover Notes
Architecture, credentials, key decisions
08
Recommended Next Steps
Immediate actions & partner criteria
Wallah We Can – GreenSchool E-Commerce Platform | Confidential
2 / 20

## Slide 3
The Mission
Why this platform exists
"Thanks to your purchase, 6 energy bars will be provided to students at Sidi Mechreg."
🌱
GreenSchool Initiative
Parents of students grow and handcraft products on farms. Every sale directly funds school supplies, meals, and energy bars for their children.
🛒
The Shop
A full e-commerce platform integrated into the WWC WordPress website. Customers browse, add to cart, and check out — all impact is tracked transparently.
📊
Impact Transparency
Every order generates a real impact record: which school benefited, how many items, funded by which purchase. Customers see their personal impact dashboard.
Wallah We Can – GreenSchool E-Commerce Platform | Confidential
3 / 20

## Slide 4
What Has Been Built
Complete system overview — Phase 1 & 2 complete
🗄️ Backend API (Django 5)
✓ 14 database models with migrations
✓ 60+ REST API endpoints
✓ JWT authentication
✓ Stripe payment integration
✓ Order email notifications
✓ Admin API (key-protected)
✓ Stock & impact tracking
🌐 Customer Frontend (Standalone HTML)
✓ Product catalogue & search
✓ Product detail + reviews
✓ Shopping cart (guest & logged-in)
✓ Full checkout flow
✓ Order history & tracking
✓ Wishlist & account settings
✓ Impact dashboard
⚙️ Admin Dashboard (Standalone HTML)
✓ KPI overview (sales, orders, impact)
✓ Product CRUD + image upload
✓ Category & producer management
✓ Order status & tracking updates
✓ Customer list & details
✓ Donation management
✓ Coupon management (UI ready)
🔌 WordPress Plugin (PHP)
✓ Shortcodes for all pages
✓ API client with 5-min cache
✓ Cart AJAX handlers
✓ Checkout & shipping logic
✓ Auth templates (login/register)
✓ Password reset flow
✓ Admin product editing in WP
Wallah We Can – GreenSchool E-Commerce Platform | Confidential
4 / 20

## Slide 5
Data Architecture
14 database models — all production-ready with migrations
Products
📋 Producer — farm producers with bio (FR/EN/AR)
📋 ProductCategory — 7 categories, hierarchical
📋 Product — multilingual, dual-currency (TND+EUR), badges, SEO
📋 ProductImage — multiple images per product
📋 ComposableBox — 'Build My Box' bundles
📋 Review — star ratings, moderated
Orders & Cart
📋 Cart / CartItem — guest & logged-in, box support
📋 Order — full lifecycle: pending→paid→shipped→delivered
📋 OrderItem — snapshot of product+price at order time
📋 ImpactEvent — real-world events funded by orders
📋 PendingCheckout — Stripe pre-payment snapshot
📋 Coupon — discount codes (model + API ready)
Customers
📋 Customer — B2C & B2B profiles, impact stats
📋 CustomerAddress — multiple saved addresses
📋 Wishlist — per-customer product wishlist
Wallah We Can – GreenSchool E-Commerce Platform | Confidential
5 / 20

## Slide 6
Customer Journey
The complete shopping experience — step by step
STEP 1
🛍️
Browse
Visit shop Explore by category, search or featured
›
STEP 2
📦
Product
View product details, images, ingredients, impact info, reviews
›
STEP 3
🛒
Cart
Add to cart Update qty Apply coupon See live impact total
›
STEP 4
📝
Checkout
Enter address (saved or new) Choose payment Credit card or COD
›
STEP 5
💳
Payment
Stripe secure payment (EUR) or cash on delivery (TND)
›
STEP 6
✅
Confirmation
Order email confirmation Order number Tracking link
›
STEP 7
👤
My Account
View orders Track shipping See my impact Manage wishlist
✓ Guest checkout supported — no account required. ✓ Logged-in customers get saved addresses, order history & personal impact dashboard.
Wallah We Can – GreenSchool E-Commerce Platform | Confidential
6 / 20

## Slide 7
Customer Account
Everything a registered customer can do in 'Mon Compte'
📊
Impact Dashboard
Personalised banner showing total purchases, total orders, and a breakdown of how many items were donated to which schools — updated after every order.
📦
Order History
Full list of all past orders with status badge (pending / paid / shipped / delivered). Click any order to see full details: items, prices, shipping address, billing address, and tracking number.
❤️
Wishlist
Save products to a personal wishlist directly from the product page. View and manage saved items in the account area.
⚙️
Account Settings
Update personal info (name, phone), default shipping address, change password, set preferred currency (TND / EUR) and language (FR / EN / AR), manage newsletter subscription.
🧾
Billing Address
B2B customers can save a separate billing address (company name, tax ID) that auto-fills at checkout — no need to re-type every order.
🔐
Password Reset
Full forgot-password flow via email link. Secure token-based reset — works independently of WordPress login.
Wallah We Can – GreenSchool E-Commerce Platform | Confidential
7 / 20

## Slide 8
Checkout — In Detail
Smart address management + dual payment method support
📦 Address Management
• Logged-in users with a saved address see it displayed instantly — no re-typing.
• Option tile 1: 'Use this address' — one click to confirm.
• Option tile 2: 'Use a different address' — expands an inline form.
• New address can be saved as default with a single checkbox tick.
• Guest users fill in the address form directly (no account needed).
🧾 Billing Address Section:
• Option tile 1: 'Same as shipping' — default, zero friction.
• Option tile 2: 'Different billing address' — expands full billing form with company name field.
• B2B customers enter company name + address for proper invoicing.
• Billing address is saved to every order for later reference.
💳 Payment Methods
💳 Card Payment (Stripe)
• Secure hosted Stripe Checkout page.
• Supports Visa, Mastercard, Apple Pay.
• Payment in EUR (customers' banks handle TND conversion automatically).
• Order created only after webhook confirms payment — no risk of unpaid orders.
💵 Cash on Delivery
• Available for Tunisian customers.
• Order placed immediately, payment at door.
• Order confirmation email sent at checkout.
• Status automatically set to 'Paid'.
🎁 Gift Packaging
• Optional add-on at checkout.
• +5 DT / +2 € — added to order total.
• Noted on order for packing team.
Wallah We Can – GreenSchool E-Commerce Platform | Confidential
8 / 20

## Slide 9
Admin Dashboard — Overview
Everything the WWC team can manage without touching code
📊 Dashboard KPIs
✓ Total revenue (TND & EUR)
✓ Orders today / this week / this month
✓ Items donated to students
✓ Top-selling products
✓ Low stock alerts
✓ API health status banner
📦 Products
✓ Add / edit / delete products
✓ Upload multiple product images
✓ Set price in TND and EUR
✓ Set B2B wholesale price
✓ Define social impact (school, qty, item)
✓ Manage stock levels
✓ Set badges: organic, handmade, vegan…
🏷️ Categories
✓ Create / rename / reorder categories
✓ 7 default categories (SOINS, NUTRITION…)
✓ Hierarchical (parent / child)
✓ Multilingual labels (FR/EN/AR)
👨‍🌾 Producers
✓ Add / edit producer profiles
✓ Upload producer photo
✓ Write bio in French, English, Arabic
✓ Track total products sold & earnings
📋 Orders
✓ View all orders with status filter
✓ Search by order number or customer
✓ Update status: paid→processing→shipped
✓ Enter tracking number
✓ System sends shipping email automatically
👥 Customers
✓ View all registered customers
✓ See B2C vs B2B type
✓ View order history per customer
✓ See cumulative impact per customer
Wallah We Can – GreenSchool E-Commerce Platform | Confidential
9 / 20

## Slide 10
Order Management Workflow
How a WWC team member processes an order from start to finish
PENDING
Order placed (bank transfer or stripe not yet confirmed)
PAID
Payment confirmed (Stripe webhook or COD marked paid)
PROCESSING
Admin confirms stock, prepares shipment (set in admin dashboard)
SHIPPED
Admin enters tracking number — email sent automatically
DELIVERED
Customer confirms receipt (or admin marks done)
CANCELLED / REFUNDED
Stock automatically restored — no manual adjustment
🤖 Automated: Stripe webhook creates order on payment · Shipping email on status→Shipped · Stock restored on Cancel/Refund
Wallah We Can – GreenSchool E-Commerce Platform | Confidential
10 / 20

## Slide 11
Impact & Donations
The social transparency engine at the heart of WWC
How Impact Is Calculated
1️⃣ Admin sets impact on each product:
→ School name (e.g. Sidi Mechreg)
→ Impact item (e.g. 'energy bars')
→ Quantity per unit sold (e.g. 6)
2️⃣ Customer buys 2 units of that product:
→ 12 energy bars recorded for Sidi Mechreg
3️⃣ Impact is captured at order time:
→ Stored permanently on the Order record
→ Cannot be changed retroactively
4️⃣ Customer sees their personal total:
→ 'You have donated 48 energy bars'
→ Breakdown by school on their dashboard
5️⃣ Admin can log real Impact Events:
→ 'March 2026: 200 bars delivered to Sidi Mechreg'
→ Visible on public Impact page
Donations Module
Separate donation flow
Customers can make direct monetary donations to specific school projects — independent of purchases.
Country & project image
Each donation project has a country flag, project description, and image shown on the donation page.
User attribution
Logged-in donors are linked to their donation for history tracking.
Admin management
Donation admin panel: view all donations, amounts, donors, dates, and project breakdown.
Public impact page
A public-facing Impact page shows cumulative donations and real events — builds trust and transparency.
Wallah We Can – GreenSchool E-Commerce Platform | Confidential
11 / 20

## Slide 12
Gap Analysis
Honest assessment of what still needs to be built
🔴 PHASE 2 — Remaining
• Composable Box builder UI — The 'Build My Box' feature: multi-step JS interface to assemble a custom box
• Email verification — Send verification email on registration; gate certain features behind verified status
• Cart count badge in WordPress header — Requires theme integration hook
• B2B billing address saved in account — Save default billing address for company customers
🟡 PHASE 3 — Business Features
• Multilingual UI switching — Language switcher widget; serve FR/EN/AR product content based on user preference
• B2B registration & approval — Dedicated company signup form + admin approval workflow
• Coupon system — Backend model is ready; need admin UI to create codes + frontend apply-coupon logic
• Live TND/EUR exchange rate — Currently hardcoded at 0.30; need daily fetch from exchange rate API
• SEO meta output — Output product meta title/description into WordPress <head>
• Google Analytics / Meta Pixel events — Track add_to_cart, purchase, view_item
🔵 PHASE 4 — Production Hardening
• PostgreSQL migration — Move from SQLite (dev) to PostgreSQL (production)
• Nginx + Gunicorn production config — Proper web server setup for api.wallahwecan.org
• SSL certificate — HTTPS for the API domain
• Media storage on S3 / Cloudflare R2 — Product images currently on server disk
• Celery async email workers — Emails currently sent synchronously; move to background queue
• Error monitoring (Sentry) — Catch and alert on production errors
• Automated backups — Daily database + media file backups
Wallah We Can – GreenSchool E-Commerce Platform | Confidential
12 / 20

## Slide 13
Roadmap — Phase 3 & 4
Work breakdown for a third-party developer
Task
Component
Effort
Priority
Notes
Multilingual UI switching
Frontend + WP
3 days
HIGH
FR/EN/AR toggle, store in cookie
B2B registration + approval
Backend + WP
4 days
HIGH
Company form, admin approval email
Coupon system — admin UI
Frontend
2 days
HIGH
Backend model already done
Email verification on register
Backend
1 day
MED
Send token on signup, gate features
Composable Box builder UI
Frontend + JS
5 days
HIGH
Multi-step selector, preview
Live TND/EUR rate
Backend
0.5 day
MED
Daily cron job, admin override
SEO meta tags in WP head
WP Plugin
0.5 day
MED
Output meta_title/description
GA4 / Meta Pixel events
Frontend JS
2 days
MED
view_item, add_to_cart, purchase
B2B billing address in account
Backend + FE
1.5 days
MED
CustomerAddress, settings page
PHASE 4 — Production Hardening
PostgreSQL migration
Backend
1 day
CRIT
Change DB engine, run migrations
Nginx + Gunicorn + systemd
Infrastructure
1 day
CRIT
Server config for production
SSL certificate (Let's Encrypt)
Infrastructure
0.5 day
CRIT
Auto-renew with certbot
S3 media storage
Backend
1 day
CRIT
django-storages + Cloudflare R2
Celery async email workers
Backend
1 day
HIGH
Redis already in requirements
Sentry error monitoring
Backend + FE
0.5 day
HIGH
Add DSN, test alerts
Automated DB backups
Infrastructure
0.5 day
HIGH
Cron + S3 offsite backup
Stripe webhook registration
Backend + Stripe
0.5 day
CRIT
Register endpoint in Stripe dashboard
Wallah We Can – GreenSchool E-Commerce Platform | Confidential
13 / 20

## Slide 14
Technical Architecture
What a new developer needs to understand on Day 1
WordPress + WWC Plugin
wallahwecan.org PHP / WordPress CMS
Standalone Frontend
HTML / Vanilla JS Served by Django at /shop/
Django REST API
Python 3 / Django 5 api.wallahwecan.org
SQLite → PostgreSQL
Database (migrate for prod)
Stripe
Payment processing EUR payments
Email (SMTP)
Order confirmations Password reset
Redis + Celery
Async task queue (configured, ready)
REST API (JSON + JWT)
──────→
Webhook Payment confirm
←───→
Tech Stack: Python 3 · Django 5 · Django REST Framework · SimpleJWT · Stripe SDK · PHP 8 · WordPress · Vanilla JS · HTML5 · CSS3
Wallah We Can – GreenSchool E-Commerce Platform | Confidential
14 / 20

## Slide 15
Technical Handover Notes
Key decisions made, files to know, and open questions
✅ Key Decisions Already Made
TND + Stripe:
Stripe charges in EUR only. TND customers pay via Cash on Delivery. Customer's bank handles any conversion.
Auth strategy:
Django JWT for shop accounts. WordPress users and Django users are separate systems. Login UI is included.
Cart sessions:
Stable session key stored in localStorage (not PHP session) — survives page reloads and browser back.
Billing address:
Captured per-order on the Order model. B2B default saved in CustomerAddress model.
Impact capture:
Snapshot at order time — impact figures cannot be changed retroactively. Protects integrity.
Admin access:
Admin frontend protected by API key auth — separate from customer JWT. Key configured in .env.
❓ Open Questions for WWC
• Hosting: VPS (Hetzner/DigitalOcean), PaaS (Railway/Render), or shared?
• Media: Store product images on S3/R2 or server disk?
• Email provider: SMTP credentials (Gmail, Mailgun, Brevo…)?
• Auth: Keep WP + Django separate, or sync logins?
• Stripe: Which account? Test mode → production switch needed.
📁 Critical Files to Know
backend/.env
All secrets: DB, Stripe keys, email, API key
backend/api/views.py
All public API logic — checkout, orders, auth
backend/api/payments.py
Stripe webhook + order creation + emails
frontend/checkout.html
Checkout UX — address tiles, payment
frontend/account.html
Customer dashboard, orders, settings
frontend/admin/index.html
Admin dashboard entry point
PLANNING.md
Full project status & roadmap
Wallah We Can – GreenSchool E-Commerce Platform | Confidential
15 / 20

## Slide 16
Effort Summary
Estimated developer days to complete the platform
~27
developer days
to complete Phase 3 & 4 (all remaining features + production hardening)
~17
developer days
for Phase 3 alone (B2B, multilingual, coupons, box builder)
~10
developer days
for Phase 4 alone (hosting, SSL, backups, monitoring, PostgreSQL)
⚠️ Assumptions: Estimates assume a mid-level full-stack developer (Django + JS) with access to the codebase, .env secrets, and server credentials. Does not include time for QA / client review cycles. A senior developer could complete Phase 3 alone in 2–3 weeks.
Wallah We Can – GreenSchool E-Commerce Platform | Confidential
16 / 20

## Slide 17
Finding a Developer Partner
What to look for and what to share with candidates
✅ Must-Have Skills
✓ Python / Django (REST API development)
✓ JavaScript (vanilla JS — no framework needed)
✓ HTML / CSS (responsive frontend)
✓ Git version control
✓ Basic Linux server administration (Nginx, systemd)
✓ Stripe integration experience
✓ Understanding of JWT authentication
👍 Nice to Have
○ WordPress / PHP plugin development
○ PostgreSQL
○ Celery / Redis
○ Multilingual web apps
📦 Share with Candidates
📄 This presentation
📄 PLANNING.md (full technical roadmap)
📄 GitHub repository access
📄 backend/.env.example (not the real .env)
📄 Access to staging server for testing
📄 Stripe test mode credentials
❓ Questions to Ask Candidates
? Have you built Django REST APIs before? Share examples.
? How do you handle Stripe webhook security?
? Can you show a multilingual Django project?
? What is your approach to production deployment?
? Do you have experience with impact/social-sector projects?
Wallah We Can – GreenSchool E-Commerce Platform | Confidential
17 / 20

## Slide 18
Recommended Next Steps
Immediate actions — in priority order
🔴 This Week
▸ Decide on hosting provider (VPS recommendation: Hetzner CX22 ~€4/month or Railway.app for easier setup)
▸ Confirm SMTP email credentials for order notifications
▸ Confirm Stripe account — switch from test mode keys to live production keys in .env
▸ Register Stripe webhook endpoint once server is up (takes 10 minutes)
🟡 Before Go-Live (Phase 2 completion)
▸ Run the platform on a staging server and do a full end-to-end test: browse → cart → checkout → email
▸ Complete email verification flow (prevents spam accounts)
▸ Decide on Composable Box builder priority — is 'Build My Box' needed at launch or can it wait?
▸ Mobile responsiveness audit on checkout and product pages
🟢 After Go-Live (Phase 3)
▸ Multilingual UI — critical for reaching Arabic and English-speaking customers
▸ B2B registration flow — important for the corporate gifts (CADEAUX D'ENTREPRISE) category
▸ Coupon/promotional codes — useful for launch campaigns
▸ Google Analytics 4 setup — understand customer behaviour from day one
Wallah We Can – GreenSchool E-Commerce Platform | Confidential
18 / 20

## Slide 19
What You Already Have
A summary of assets ready to hand to a developer
Backend Assets
✓ Complete Django 5 project (production-grade structure)
✓ 14 database models + all migrations written
✓ 60+ API endpoints (products, orders, customers, payments, admin)
✓ JWT authentication system fully wired
✓ Stripe Checkout + webhook integration complete
✓ Order confirmation + shipping notification emails
✓ Stock management with automatic restore on cancellation
✓ Admin API with API key protection
✓ Sample data population commands for testing
✓ .env.example documenting every required variable
Frontend Assets
✓ Product catalogue page (search, filter, pagination)
✓ Product detail page (images, reviews, impact, add-to-cart)
✓ Shopping cart (guest + logged-in, live totals)
✓ Checkout (smart address tiles, billing, Stripe + COD)
✓ Order success + order detail pages
✓ Customer account (orders, wishlist, impact dashboard)
✓ Account settings (profile, address, password, preferences)
✓ Login + Register + Password Reset pages
✓ Admin dashboard (products, orders, customers, donations)
✓ Impact + Donate public pages
Documentation
✓ PLANNING.md — complete technical roadmap
✓ This presentation — non-technical overview
✓ All code commented and structured
✓ API endpoint list in urls.py
✓ Inline code comments throughout
WordPress Plugin Assets
✓ Full WP plugin with all shortcodes
✓ API client class (caching, auth, all resources)
✓ Cart, checkout, auth PHP classes
Wallah We Can – GreenSchool E-Commerce Platform | Confidential
19 / 20

## Slide 20
🌿
Every purchase plants a seed.
Every seed feeds a student.
The platform is ready. The mission continues.
Platform Repository: GitHub — wwc_web_new
Technical Documentation: PLANNING.md
Contact for handover: [your contact here]
Wallah We Can · GreenSchool Initiative · 2026
Wallah We Can – GreenSchool E-Commerce Platform | Confidential
20 / 20